## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
A1 | User registion and login in | As parent, I want to register a new account with appropriate account name and code. So I can login in my account with the corresponding account name and code. | very high | 1 | 1.make sure the user can regi ster their own account correctly 2.make sure the user can login in their own account with the account and code |  | 2024.3.28 | 2024.4.11
A2 | Virtual bank account management | As parent and children I want to manege the virtual bank account, such as creating a new bank account, deleting bank account or choosing their bank type. So I can use the virtual bank to manage my money. | very high | 1 | 1.make sure the user can create new accounts. 2.make sure that users can select account types. |  | 2024.3.28 | 2024.4.11
B1 | Balance tracking | As a child I want to display the balance of my bank account so I can see how many money I have and manage them. | very high | 1 | 1.make sure the child can see the balance of the bank account |  | 2024.3.28 | 2024.4.11
B2 | Deposit the money | As a child I want to deposit money into my bank account so I can save more money. | very high | 1 | 1.make sure the child can deposit their money into the bank account. |  | 2024.3.28 | 2024.4.11
B3 | Withdrawal of the money | As a child I want to withdraw the money from my bank account so I can use the money when I need them. | very high | 1 | 1.make sure the child can withdraw their money from their bank account. 2.make sure that the child can not withdraw the amount of money which is more than the deposit in the bank account. |  | 2024.3.28 | 2024.4.11
C1 | Task setting | As a parent I want to set a task and the rewards. So my child can get rewards if they finish their work. | very high | 1 | 1.make sure the parents can set tasks to children and they can change the rewards as they with. |  | 2024.3.28 | 2024.4.11
B4 | Task accepting | As a child I want to accept the task and submit the task to get the rewards. | high | 2 | 1.make sure the child can submit the task when they finish them. |  | 2024.4.12 | 2024.5.1
C2 | Task checking | As the parents I want to check whether the child has finished the task and pass the submission if child finished the task. So I can check whether the child is lying if they do not finish the task and want to get the rewards. | high | 2 | 1.make sure the parents can review submission from the kids and judge whether it can be passed. |  | 2024.4.12 | 2024.5.1
E1 | Transcation hisroty | As the bank administrator I want to check all the transcation history of all the accounts so I can check all the bank accounts. | high | 2 | 1.make sure the bank administrator can see all the bank list. 2.make sure the bank administrator can select one of the bank account and see all the transcation history. |  | 2024.4.12 | 2024.5.1
C3 | Saving goals | As parent I want to set some saving goals to the child so they can develop a good habit of saving money. | high | 2 | 1.make sure the parents can set the saving goals. 2.make sure the parents can change the saving goals. |  | 2024.4.12 | 2024.5.1
E2 | Administrator registion and login in | As bank administrator I want to create another administrator account and login in it with the corrseponding account name and code so I can manage the bank account more easily. | high | 2 | 1.make sure the administrator can create and login in other accounts. |  | 2024.4.12 | 2024.5.1
C4 | Transcation history of parents | As parents I want to see the transcation history of my child account so I can see how they spend their money. | medium | 3 | 1.make sure the parents can see their children's transcation history. |  | 2024.5.5 | 2024.5.10
C5 | Parental Insight Reports | As parent, I want to receive monthly insight reports on my child's saving and spending habits so that I can guide them better. | Medium | 3 | 1.receive a detailed report showing savings, spending, and task completion stats. |  | 2024.5.5 | 2024.5.10
B5 | Educational Video Rewards | As a child, I want to watch educational videos about money and earn virtual money for completing them to improve my financial literacy. | Medium | 3 | 1.watch an approved financial education video and answer a quiz question correctly to earn virtual money. |  | 2024.5.5 | 2024.5.10
C6 | Task Customization by Parents | As parent, I want to customize tasks with different difficulty levels and rewards to adapt to my child’s growing capabilities | medium | 3 | 1.create tasks with adjustable difficulty and reward settings, allowing for a tailored experience as children grow. |  | 2024.5.5 | 2024.5.10
C7 | Customizable Alerts for Parents | As a parent, I want to receive customizable alerts about my child's account activity so I can stay informed about their progress and intervene when necessary. | High | 2 | 1.set up and receive alerts for specific activities, such as goal completion, large transactions, or low balance |  | 2024.4.12 | 2024.5.1